## Cover
Business Analysis Plan
Project Name | WeGotBank
Author | Sertina Augustine
Version | 1
Date | 2021-09-22
Revision History
Revision # | Content Changed | Change Date
1 | Initial Version | 2021-09-22

## Requirements Stakeholder List
Requirements Stakeholder List
Name | Role | Approve/ Review Requirements
Mxxx Lxx | Business Subject Matter Expert | Approve
Rxxx Mxxx | Business Subject Matter Expert | Review
Cxxx Oxxx | Business Subject Matter Expert | Review
Rxxx Rxxx | Project Manager | Review
Txxx Kxxx | BA Manager | Review
Cxxx Pxxx | BA Manager | Review

## Business Analysis Work Plan
Business Analysis Work Plan
# | Task and Milestones | Technique | Start Date | Due Date | Status
1 | Stakeholder Requirements
1.1 | Review Business Needs | Document Analysis | 2021-09-20 | 2021-09-20 | Complete
1.2 | Research Analysis | Case Study, WordPress, Ui Path Analysis | 2021-09-21 | 2021-09-23 | Complete
1.3 | Attend Team Touchpoint meeting | Meeting | 2021-09-23 | 2021-09-23 | Complete
1.4 | Draft High Level Requirements | Business Context Diagram, HLRs | 2021-09-24 | 2021-09-25 | Complete
1.5 | Review HLRs | Review Workshop | 2021-09-26 | 2021-09-26 | Complete
2 | Solution Requirements - Iteration 1
2.1 | Draft PDD | Document Analysis, PDD | 2021-09-26 | 2021-10-09 | Complete
2.2 | Attend Team Touchpoint meeting | Meeting | 2021-09-27 | 2021-09-27 | Complete
2.3 | Prepare draft Process Flow Maps (AS IS & TO BE) | Document Analysis, Process Flow Maps | 2021-09-29 | 2021-10-09 | Complete
2.4 | Attend Team Touchpoint meeting | Meeting | 2021-10-04 | 2021-10-04 | Complete
2.5 | Review PDD & Process Flow Maps | Review Meeting | 2021-10-10 | 2021-10-11 | Complete
2.6 | Attend Team Touchpoint meeting | Meeting | 2021-10-04 | 2021-10-04 | Complete
2.7 | Elicit Process Flow Maps for WeGotBank | Elicitation Workshop | 2021-10-12 | 2021-10-12 | Complete
2.8 | Conduct Interview for WeGotBank | Interviews | 2021-10-12 | 2021-10-12 | Complete
3 | Solution Requirements - Iteration 2
3.1 | Update Process Flow Maps based on elicitation | Process Flow Maps | 2021-10-13 | 2021-10-23 | Complete
3.2 | Attend Team Touchpoint meeting | Meeting | 2021-10-18 | 2021-10-18 | Complete
3.3 | Review Process Flow Maps | Review Workshop | 2021-10-24 | 2021-10-24 | Complete
3.4 | Attend Team Touchpoint meeting | Meeting | 2021-10-25 | 2021-10-25 | Complete
3.5 | Distribute Process Flow Maps for WeGotBank | Use Case Diagram | 2021-10-26 | 2021-10-26 | Complete
3.6 | Business Process Flow walkthrough | Meeting | 2021-10-28 | 2021-10-28 | Complete
4 | Solution Requirements - Iteration 3
4.1 | Draft Low Level Mockups | Sketches | 2021-10-29 | 2021-10-31 | Complete
4.2 | Attend Team Touchpoint meeting | Meeting | 2021-11-01 | 2021-11-01 | Complete
4.3 | Draft WordPress Collaterals | WordPress | 2021-11-02 | 2021-11-19 | Complete
4.4 | Update PDD | PDD | 2021-11-06 | 2021-11-14 | Complete
4.5 | Attend Team Touchpoint meeting | Meeting | 2021-11-08 | 2021-11-08 | Complete
4.6 | Review Final PDD & WordPress Collaterals | Review Analysis | 2021-11-14 | 2021-11-19 | Complete
4.7 | Attend Team Touchpoint meeting | Meeting | 2021-11-18 | 2021-11-18 | Complete
4.8 | Distribute PDD & Collaterals | Distribution | 2021-11-20 | 2021-11-20 | Complete
4.7 | Attend Team Touchpoint meeting | Meeting | 2021-11-22 | 2021-11-22 | Complete
4.9 | PDD walkthrough & Collaterals chekpoint | Meeting | 2021-11-23 | 2021-11-23 | Complete
5 | Solution Requirements - Iteration 4
5.1 | Build POC | Ui Path, WordPress | 2021-11-24 | 2021-12-05 | Complete
5.2 | Attend Team Touchpoint meeting | Meeting | 2021-11-29 | 2021-11-29 | Complete
5.3 | Update & Review POC | Ui Path, WordPress | 2021-11-30 | 2021-12-06 | Complete
5.5 | Final POC Demo | Meeting | 2021-12-07 | 2021-12-07 | Complete